## Copy of Estimation (hidden)
Requirement |  |  | Ref: https://docs.google.com/presentation/d/1VGMk8PpegoMBIemdqtWOqxsp2SzU3BRiObF52Sxl5vU/edit#slide=id.g237a986052f_2_5 Customer A has a PHP/Web application, hosted on Linode/other cloud, traditional development commitment with GitHub/other version control, small company, two developers. Manual testing/no testing. Customer A wants to put it into a new, scalable containerized environment with automated build/deployment/testing using any range of tools. Customer A is trying to save time, speed up feature releases and speed up code through monitoring and revisions.
Assumption |  |  | General Assumptions 1. App should be Cloud native, means it should not have local file dependencies 2. Not suitable for wordpress and other traditional apps 3. Cloud native PHP applications can be built on frameworks like Laravel without local file dependencies using database and object storage for storing data & assets Applications that can be single handedly deployed using Git Commits can be considered for DevOps - For instance, in Drupal, we can export configurations ( Database Schema, Post Types, etc ) and commit it to GIT. This can be pulled and deployed on multiple instances without needing any manual efforts. - Some application, such as Wordpress, which is dependent on one index.php file can use DevOps, but the Deployment would be very difficult in future. So they are not preferred. - Devops is mainly fast tracking the deployment process for development completed applications. So it doesn’t need the same developer expertise for DevOps implementation. Other Assumptions - This use case has 2 developers working for the customer. In case of any code issue, the client developers can be contacted for assistance. - Software Development is independent of DevOps. - The DevOps Process -- Setting up a Docker Container with the required modules ( PHP, Apache, MySQL, etc ) --- Set up Volumes to use S3 Bucket or similar --- Set up Networking inside Docker for Security -- Automated Build -> Continuous Integration (CI) -- Automated Deployment -> Continuous Delivery (CD) -- Automated Testing -> Integration with Selenium or similar testing tools -- Client has on-premises Development team
Efforts
I | Design Effort |  | 0
II | Development Effort |  | #REF!
III | Deployments & Verifications |  | #REF! | #REF!
TOTAL ( I+II + III ) |  |  | #REF!
Project Cost | [5 empty] | Start
I | Design Cost @$35/hr |  | 0 | 35 | <<- Change Design Rate
II | Development Cost @$35/hr |  | #REF! | 35 | <<- Change Dev Rate
TOTAL |  |  | #REF! |  |  | 99
Development Estimation Split-up
A | Total QA effort |  | #REF! | #REF!
B | Total Management effort |  | #REF! | #REF!
C | Total Development Effort |  | #REF! | #REF!
| Total Development Effort with Additional Effort factored A+B+C |  | #REF! | #REF!
Timeline
Total Days |  | #REF! | Days
Resources Allocated |  | 3 | Nos
Start Date |  | 2023-08-07
Total Project Duration |  | #REF! | Days
Expected End Date |  | #REF!
Weeks |  | #REF! | Weeks
Month |  | #REF!
Detailed Estimation Split-up
Sl No |  |  | Process Steps | Explanation | Total DevOps Effort | Total Effort
1 | Discovery | Requirement analysis | Requirment collection | Get current issues faced, what are expectations from new structure.
|  |  | Review the current deployment documentation | To study how the application is currently deployed and how the various components work together
|  |  | Analyzing application for migration to docker | Identify resources required database, session storage, CDN etc
2 | Design | Architecture design | Designing the Docker application and components | Build the docker image to match the application requirement | 1 | #REF!
|  |  | Design the AWS infrastructure with all components | Will identify all the AWS components required to build the architecture and how they will interact. | 4 | #REF!
|  |  | Design the ECS cluster | Identify what type of cluster needs to be setup (Fargate/EC2) | 1 | #REF!
3 | Infrastructure implementation | Setting up the Cluster | Configure the cluster | Setup the ECR | 0.5 | #REF!
|  |  |  | Setup the Task Definition | 0.5 | #REF!
|  |  |  | Setup the ECS stage and prod clusters | 0.5 | #REF!
|  |  | Configure the load balancer | Setup the Load balancer and target group | 0.5 | #REF!
4 | Automated Build | Setting up the Pipeline | Configuring AWS CodePipeline | Set up the Source stage | 0.5 | #REF!
|  |  |  | Setup the steps of the Pipeline | 0.5 | #REF!
|  | Setting up CodeBuild | Compile a script to be used with codebuild | Compose the buildspec file for CodeBuild | 0.5 | #REF!
5 | Automated Deployment - Stage | Deployment to stage | Setting up Deploy stage to AWS ECS | Setup the deploy stage to deploy to stage cluster | 0.5 | #REF!
4 | Automated Testing | Creation of Test Cases. | The usual process starts with the tester studying the business requirements to isolate a set of user stories. These user stories help represent the business requirements – what a person using the product would like to be able to do. This, in turn, helps cater to a series of user personas, and create a number of test scenarios. | Creating a workflow of the system | 7 | #REF!
Analyse various use cases for the testing
Analyse various users and respective roles
Analyse various users and respective roles
|  |  | Once the test scenarios are framed, a set of industry-wide best practices are followed to frame these scenarios into a sequence of actions that can help verify a particular functionality. This is what is known as a Test Case. | Once the test scenarios are framed, a set of industry-wide best practices are followed to frame these scenarios into a sequence of actions that can help verify a particular functionality. This is what is known as a Test Case. | 7 | #REF!
5 | Release | User Acceptance Testing | User Acceptance Testing ( UAT) | A period of business days will be allotted for the client to the portal internally. Feedbacks and bugs may be reported at the time, which shall be collected and acted upon by Bobcares.
|  |  | Bug correction if any after UAT | If any bugs are identified, Bobcares shall work on fixing them and release a pre-beta release | 8 | 8
6 |  | Live Release | Releasing the bugs and enhancements to a live environment | The app will be deployed to app store accounts shared with Bobcares and also on a server for the portal | 12 | 12
END
10 | Environment | Container Architecture | Create shared S3 Storage | A shared storage needs to be setup so that the containers can be independent of storage locations, and to ensure data persists. | 7 | #REF!
|  |  | Create a network | Containers needs to communicate with the outside works by means of network. This is also required for inter-application networking. | 7 | #REF!
|  |  | Create a Docker Container | A development environment needs to be set up for performing the build operations | 7 | #REF!
11 | Automated Build | Setting up Pipeline | Configuring AWS CodePipeline | Set up the Source Provider
Set up the buld provider
Set up the deployment provider
|  |  | Connect a Source Repository | Setting up AWS CodeCommit or other GIT Repositories to work with the Pipeline
12 |  | Setting up CodeBuild | Compile a script to be used with codebuild | Once a code is received on the pipeline, it needs to be built and/or processed before deploying
|  |  | Seting up the action | Once the script is compiled, it can be used to build a temporary environment (such as windows, linux ) and execute the script
|  |  | Setting up Post-build actions | Any actions that needs to be run after the build process, needs to be set up here

## React-Django-Postgres
Efforts(hrs)
I | Design Effort |  | 6
II | Implementation Effort |  | 15.5
III | Testing |  | 0
TOTAL ( I+II + III ) |  |  | 22
Project Cost |  |  |  | Per hour rate
I | Planning Cost |  | 180 | 30
II | Implementation Cost |  | 465 | 30
III | Automated Testing Cost |  | 0 | 30
TOTAL |  |  | 645
Timeline - Technical (Overall)
Total Days |  | 3 | Days
Resources Allocated |  | 1 | Nos
Start Date |  | 2023-09-01
Total Project Duration |  | 3 | Days
Expected End Date |  | 2023-09-06
Weeks |  | 1 | Weeks
Month |  | 0 months 5 days
Detailed Estimation Split-up | [6 empty] | Effort multiplyer | 1
Sl No |  |  | Process Steps | Explanation | Total DevOps Effort | Total Effort
1 | Design | Frontend | Design the VPS for frontend | Discuss the application requirement and design the VPS to host the Reach frontend | 2 | 2
|  | Backend | Design the VPS for backend | Discuss the application requirement and design the VPS to host the Django backend | 2 | 2
|  | Database | Design the VPS for database | Discuss the application requirement and design the VPS to host the Postgress database | 2 | 2
2 | AWS Setup | AWS Account | Create AWS account | Set up AWS accounts and permissions. | 1 | 1
|  | AWS Infrastructure Setup | Setup network and firewall | Default VPC and 3 Subnet (2 public and 1 private), Create a Private Route Table, Create a NAT Gateway, Configure Route Table for Private Subnet, Subnet Association,Create security group | 1.5 | 1.5
|  | Setup user | Create User | Create IAM User (Client/developer), Specify permission according to requirement | 0.5 | 0.5
3 | Code Repository Setup | Source setup | Setup GitHub account | Create a Git repository for your application (e.g., GitHub, Bitbucket). | 1 | 1
|  |  | Configure the repository | Configure version control, branching strategy and Git hooks. | 1 | 1
4 | IaC | Terafform template | Desiging Terraform template for launching the instances in the development environment | Install Terafform and code the YAML file to deploy the instances for the dev environment | 3 | 3
5 | Application | Setting Up the React Application | Create React Application in public subnet instance | Install Node.js , Create Project Directory, Create-react-app, Start the React app | 2 | 2
|  | Setting Up the Django Application | Create Django Application in instance | Create Project Directory, Install Python and Set Up Virtual Environment, Create a Django Project, Edit the settings.py file: | 2 | 2
6 | Database | Setup Database | PostgreSQL Database Setup on Private Instance | Install PostgreSQL,Configure PostgreSQL, Restart PostgreSQL | 2 | 2
|  | Setup graphical interface for database | Installing and Configuring pgAdmin4 | Install pgAdmin4,Access pgAdmin4, Connect to the Database Server | 1.5 | 1.5